## Note
#VALUE! | This checklist is intended to serve as a general guide for municipalities administering Local Action Units (LAUs) under the Massachusetts Local Initiative Program (LIP). It outlines a typical set of responsibilities and best practices observed across communities but may not reflect every scenario or legal requirement. The duties described are suggested based on guidance from the Executive Office of Housing and Livable Communities (EOHLC), Massachusetts Housing Partnership (MHP), and the experience of participating municipalities. However, roles and procedures may vary depending on local staffing, permitting processes, and project-specific circumstances. Municipalities should consult with legal counsel, EOHLC, or their Shared Housing Services Office (SHSO) for project-specific requirements or to confirm compliance with the latest state guidelines. This checklist does not replace official regulations or documentation required for SHI inclusion or LIP approval.

## LAU Checklist
Phase | Municipal Duty | Suggested Responsible Party | Status | Notes / Link to correspondence / Link to documentation
1. Confirm Eligibility | Confirm local action enabling affordable units (e.g., inclusionary zoning, CPA funds, special permit). | Planning/Community Development/SHSO
| Confirm target AMI, unit mix, integration, and design standards align with LIP/760 CMR 56 guidelines | Planning/Community Development/SHSO
| Confirm affordability term (preferably in perpetuity, minimum 30 years) | Planning/Community Development/SHSO
| Add permit conditions that require LAU compliance and specify deadlines for LIP LAU submission. | Planning Board/Council, Planning Staff |  | At or just before local land use approval; prior to building permit issuance
2. Pre-Application Coordination | Early coordination with EOHLC LIP staff and AFHMP review | Planning/Housing/SHSO
| Share draft affordability conditions and project summary and confirm AFHMP review process and timing | Planning or Housing Staff/SHSO |  | LIP Approval of the Affirmative Fair Housing Marketing and Resident Selection Plan must occur before marketing and resident selection.
3. LAU Application Submission | Prepare and submit LAU Application to EOHLC (often supported by developer) | Municipal Planning or Housing Dept./SHSO |  | Typically, special permits and other land use approvals issued by a municipality include specific deadlines by which the developer must submit their LAU application to EOHLC.
| Municipality reviews and signs application per LIP requirements. | Municipal Planning or Housing Dept./SHSO |  | Include: – Documentation of municipal action (e.g., special permit, CPA funds, land donation) – Long-Term Use Restrictions: LIP Regulatory Agreement (rental/ownership), HOME covenant if applicable, and/or deed rider (ownership) – Sponsor legal documents: Good Standing certificates, trustee authorizations, mortgagee consents – Copy of approved site plan – Master Deed (condo only) – Lease and addendum + LHA Utility Allowances (rental only) – AFHMP including ads, flyers, eligibility requirements, lottery forms, local preference justification, and outreach plan.
| Developer prepares a redlined version of the Regulatory Agreement and submits with the LAU application. Application package submission to EOHLC | Municipal Planning or Housing Dept./SHSO |  | Submit the LIP LAU for municipal approval before the first building permit; building permits should indicate the building ID and number of units (affordable units need not be identified).
4. Regulatory Agreement Preparation, Execution, and Recording | EOHLC reviews and approves. Developer and Municipality execute final Agreement. Developer sends executed copy to EOHLC for signatures. | Developer; Municipality; EOHLC
| EOHLC returns the agreement for recording at Registry of Deeds. The recorded Agreement places the affordable housing restriction on the property. | Developer; Municipality; EOHLC |  | For Ownership LAUs: Units are eligible only after homes have been sold with the deed rider attached and recorded.
5. Apply to Include Units on SHI | Confirm the project meets SHI requirements and timelines; avoid lapses (e.g., >1 year post‑zoning approval without building permits; >18 months post‑permit without occupancy) | Municipality (with Developer support); EOHLC SHI Coordinator |  | Ownership LAUs : Eligible only after sale with recorded deed rider Rental LAUs : Eligible after building permits and recorded Agreement
| Submit the SHI Request Form to EOHLC with all required supporting documentation. | Municipality (with Developer support); EOHLC SHI Coordinator |  | Link to EOHLC SHI Form to request new units - https://www.mass.gov/doc/requesting-new-units-form-0/download
6. Post-Occupancy Monitoring | Assign a staff member, SHSO/RHSO, or third-party monitor | Municipality; SHSO/RHSO; Monitoring Agent;
| Establish annual reporting schedule. Coordinate rent increase approvals and income verifications with developers | Monitoring Agent / SHSO
| Review resale processes and ensure compliance with deed riders. Ensure Fair Housing compliance in resales and marketing activities. | Monitoring Agent / Municipality
| Maintain records of annual certifications and rent schedules | Monitoring Agent; Developer |  | Utilize standardized, ideally digital forms instead of emails/mail for record keeping.
| Maintain contact and oversight of developer/property manager for ongoing compliance. | Municipality or SHSO |  | Refer to resources section of the toolkit for templates.